## Possession Timeline
Sunrise Heights Premium Apartments — Construction & Possession Timeline
Milestone | Description | Target Month | Tower(s) | Status | Remarks
Land & Approvals | RERA registration, plan sanction, title clearance | Jan–May 2023 | All | Completed | All approvals in hand
Excavation | Foundation pit excavation and soil testing | Jun–Aug 2023 | T1–T4 | Completed | Geotechnical report submitted
Foundation | Pile foundation, raft slab casting | Sep–Dec 2023 | T1–T4 | Completed | 100% pile load test done
Basement Slab | Basement B2, B1 slabs + waterproofing | Jan–Mar 2024 | T1–T4 | Completed | Parking slab ready
Ground Floor Slab | Podium slab, ground floor framing | Apr–Jun 2024 | T1–T4 | In Progress
Floors 1–5 | Column, beam, slab casting for floors 1–5 | Jul–Oct 2024 | T1–T2 | In Progress
Floors 6–10 | Column, beam, slab casting for floors 6–10 | Nov 2024–Feb 2025 | T1–T2 | Upcoming
Floors 11–15 | Column, beam, slab casting for floors 11–15 | Mar–Jun 2025 | All | Upcoming
Floors 16–22 (Top) | Top floor slab and terrace waterproofing | Jul–Oct 2025 | All | Upcoming
Brick Work | Internal and external masonry across all towers | Aug–Nov 2025 | All | Upcoming
Plastering & MEP | Internal plaster, electrical, plumbing rough-in | Sep 2025–Feb 2026 | All | Upcoming
Internal Finishes | Tiling, painting, kitchen, bathroom fixtures | Jan–Jun 2026 | All | Upcoming
External Facade | External plastering, texture paint, glazing | Mar–Jul 2026 | All | Upcoming
Amenities & Landscaping | Clubhouse, pool, gym, gardens fit-out | Jun–Sep 2026 | Common | Upcoming
Pre-OC Inspection | BBMP inspection, fire dept. clearance, lift inspection | Oct 2026 | All | Upcoming
Occupancy Certificate | OC obtained from BBMP | Nov 2026 | All | Upcoming
Possession Handover | Keys handed over to buyers; society formation | Dec 2026 | All | Upcoming | RERA committed date